Terms of Reference for End-Term Evaluation of project:

Strengthening the resilience of vulnerable Jordanians and refugees through Inclusive Community Center

Contents

1.	Evaluation Summary	3

2.	Project Background and Description	4

3.	Evaluation Objective and Intended Use	5

4.	Limitations	5

5.	Target Groups and learning	5

6.	Evaluation Questions	6

7.	Methodology	8

8.	Management Responsibilities and Evaluation Team	9

9.	Deliverables	9

10.	Evaluation Schedule	11

11.	Payment Mode	11

12.	Applications	12

13.	Documents	13

Terms of Reference for Evaluation

## Evaluation Summary

| Project ID and Program/Project Name | P10351 Strengthening the resilience of vulnerable Jordanians and refugees through Inclusive Community Center |
| --- | --- |
| Name of Partner Organisation/s | King Hussein Foundation (KHF) |
| Project start and end dates; phase of project if applicable | 01-01-2023 - 28-02-2025 |
| Evaluation Purpose | Assessment of overall results of project for accountability purpose and organisational learning |
| Evaluation Type | Final Evaluation |
| Contracting organisation/contact person | CBM Christoffel Blinden Mission Christian Blind Mission e.V. (CBM) Eastern Mediterranean Program Musab Raddad (Country Programme Officer) |
| Primary Methodology | Tbd, to be outlined in proposals of potential evaluation teams |
| Proposed Evaluation Start and End Dates | November.2025 –December.2025 (Up to 20 working days) |
| Anticipated Evaluation Report Release Date | 20.12.2025 |
| Recipient of Final Evaluation Report | CBM, KHF |

## Project Background and Description

Overall objective:

Contribute to the long-term strengthening of the resilience capacity and improving the quality of life of refugees and vulnerable Jordanians in Amman (East Amman).

Project outcome:

Output 1: Refugees, vulnerable Jordanians and people with disabilities have access to quality inclusive health and rehabilitation services

People with disability, especially women and girls with a disability in Jordan face limitations in participating in society due to challenges in accessing educational and healthcare services, and a lack of awareness and education among caregivers and community members’  on how to address the needs of people with disabilities. To improve participation of people with a disability , IFH will improve in a first step their access to health, and rehabilitation services .

KH\IFH CBID volunteers will use a screening form of Washington group questions to collect the data and sort the beneficiaries according to their level of need to receive further services. The case manager will gather further information that is needed including the financial situation severity of disability and possibilities of improvement, creating a point system which will inform a prioritization in referral   to proper services including hearing, vision, medical consultation, speech, special education, physical therapy, occupational therapy.

Output 2: Refugees, vulnerable Jordanians and people with disabilities have increased chances to gain employment through accessing business and livelihood training

While people with disability, especially women with disability, face a number of challenges accessing the labor market in Jordan, the IFH case manager will refer beneficiaries from result 1 to the Community Development Institute  which forms part of  Noor Al Hussein Foundation since 1989,  improving the livelihoods and resilience of women, youth and the marginalized by creating job opportunities, building  institutional and entrepreneurial capacities of individuals and community-based organizations, accessing seed money and improving community infrastructure.    Through the provision of business development training including life skills training, career readiness for employment training, Entrepreneurship principles training workshop and feasibility study preparation training, as well as  conducting  job fairs, beneficiaries with disabilities are better equipped with skills that are on demand in the labor market.

Output 3: Refugees, people with disabilities and vulnerable Jordanians advocate actively for their rights in the community

Promoting rights is one of the core components within this project. People with disabilities and their caregivers as well as people without disability who are interested can be involved in expanding their capacity on how to advocate for the rights of people with disabilities within the community. This will be done by enrolling them in specialized training, followed by initiatives that are planned and implemented by disability leaders. During the project implementation a project steering committee will be formed which comprises members of people with disabilities, OPDs representatives, community leaders and other members.  The role of this committee is to ensure that project activities reflect the real needs of the community and implement them accordingly.

## Evaluation Objective and Intended Use

The purpose of this End-term evaluation is to assess the overall performance of the project implemented from 01-01-2023 to 28-02-2025. Therefore, the End-term evaluation shall review and assess the project in terms of its achieved objectives and outcomes, and identify successes, as well as possible gaps and challenges.  The lessons learned and recommendations will inform future programming and strategic planning by CBM and its partners. The evaluation will also support accountability to all stakeholders, service users, implementing partners, community members, and the government sector, including relevant ministries and governorates involved in national implementation and monitoring—by providing a transparent assessment of the outcomes achieved and the resources utilized. An Executive Summary and graphical depictions of findings, together with a limited number of useful recommendations, shall allow stakeholders to use it for adjustment and learning.

Finally, the evaluation will be a valuable resource for other stakeholders involved in the project. It will provide an overview of the project's various components and offer insights into potential areas for improvement moving forward.

## Limitations

- Regional security conditions and political instability. Evaluation activities must remain flexible and adaptable, particularly in areas near borders or within refugee camps. Coordination with KHF is advisable.

- Coordination and bureaucracy of governmental entities, which could cause delay in response for meetings with officials. Coordination with KHF is advisable.

- Cultural and social sensitivity regarding gender and disability. Cultural norms may influence the willingness of participants to discuss gender-based issues or disability inclusion, particularly in more conservative or rural communities. It is advisable to apply culturally sensitive approach and ensure informed consent, privacy, and confidentiality.

## Target Groups and learning

The main target group, including persons with disabilities, will have the opportunity to provide essential feedback and participatory input. This is vital to ensuring that future project implementation is more closely aligned with their needs, expectations, and priorities.

Direct target group:

A total of 1704 beneficiaries will be in a way or another directly benefiting from the project

1271 people will benefit from the rehabilitation and Health services, 7 staff members will be trained on delivering rehabilitation and health services, committee of 10 members will be formed and 200 people will access medical services and information on the medical campaign days.

200 people will benefit from the initiatives conducted by the people with disability leaders

Indirect target group:

1704*4.7 (the percentage stands are the average of Jordanian and Syrian family members as they will be indirectly affected by the project services) = 78008.8 beneficiaries.

## Evaluation Questions

The guiding questions for the evaluation are based on the OECD (Organization for Economic Cooperation and Development) DAC (Development Assessment Criteria) evaluation criteria of relevance, coherence, effectiveness, efficiency, impact, and sustainability.

In line with Disability Inclusive Development (DID) standards, the end-term evaluation will not only assess the engagement of persons with disabilities within different phases of the project cycle. It will also actively include persons with disabilities and OPDs in the evaluation process. Other areas the evaluation needs to consider are Gender and Child Safeguarding as mandatory areas of enquiry. The next table provides further details.

Suggested guiding questions

RELEVANCE: Assessing the relevance of a completed project involves evaluating how well its outcomes align with its initial objectives and the broader context it was intended for.

- Did the project address the significant needs of the stated target groups? Have different needs of persons with disabilities been addressed? - To what extent have the objectives of the project been valid considering the need and priorities of the participants/ target group, partner organisations and local/national conditions? - Are the objectives realistic and relevant given the available resources and conditions? - Are the results still relevant for similar stakeholder needs?

COHERENCE – This point measures how well does the project fit in the broader national and international context.

- To what extent are the project’s design, delivery and results coherent with international laws and commitments to disability rights, gender equality and rights, including the UNCRPD, CEDAW3, and the 2030 Agenda? - To what extent does the intervention support national legislation and initiatives that aim to improve equality and human rights?

EFFECTIVENESS: This measures to which extent the project is achieving what it set out to do, including but not limited to the quality of planning, indicators, implementation as well as target achievement and ownership by partner(s)

- To what extent have project activities improved supply and access to inclusive community-based education and rehabilitation services East Amman for persons with disabilities up to now? What are the challenges & achievements in this regard? - Have the target values been met according to plan? What has affected the achievement of those results? - What are the major factors influencing the achievement or non-achievement of the project’s outcome/outputs? - What monitoring systems have been used during implementation and how far have they captured different results for groups of persons (male/female, with and without disabilities)? Were data collected and disaggregated according to gender, age and disability? - To what extent are persons with disabilities able to advocate for their rights in strategic planning?

EFFICIENCY: This point measures the outputs (results) in relation to the inputs (expenditures, both financial, staffing, time) and whether funds are used in the most cost-effective way to achieve the desired results. This generally requires comparing alternative approaches to achieve the same outputs to conclude whether the most efficient process has been adopted.

- Is the project being implemented in the most efficient way compared to possible alternatives? Is duplication with other actors’ work in a similar field/the same geographical area avoided (or are synergies used)? - Have there been significant delays to implementation, and if so, what were these and why? Did the partner recruit project staff that meets the needs of the project? Was there any staff fluctuation, and what were the causes? How efficient was the entire process of planning and implementation? Were plans of activities delayed or adjusted to actual needs? How was the project managed? - Was the technical execution of the approach to CBID/CBR chosen by the project adequate and the most efficient intervention strategy? Were the financial resources and other inputs efficiently (most economically) used to achieve results? Have, in general, the project funds been used strategically and efficiently? Are there procedures employed by the partner organizations that ensure efficient use of the project funds, and have these procedures been fully understood and followed by the project staff in the implementation of the project? Are existing learning processes such as reflection and internal review used sufficiently to keep the project plan updated?

Contribution to change (impact): This point assesses the positive and negative consequences of the project activities, direct and indirect, intended and unintended. Achievement of the overarching developmental goals as well as structural formations shall be measured as well.

- What are the key changes – both positive and negative – that the programme brought into the lives of beneficiaries, their family members and the community? How is the project perceived by the community and Organizations of People with Disabilities (OPDs)? What positive/negative effect(s) were unintended or not expected? - How has the project contributed to building more inclusive communities, particularly for persons with different types of disabilities, refugees with disabilities, and those in rural areas? To what extent has awareness of the rights of persons with disabilities and issues related to psychosocial health increased among the target group? - Is the target group able to apply Community Based Inclusive Development (CBID) and Community Based Rehabilitation (CBR) in their daily work, or to what extent might they be able to do so by the end of the project? What challenges and successes have emerged? Has knowledge of the UN Convention on the Rights of Persons with Disabilities (UNCRPD) improved, and how is this being applied in practice? have the interventions created a sense of ‘ownership’ of the project’s goals among key stakeholders?

Sustainability: This point refers to the probability of an intervention to continue delivering benefits beyond the project period. The sustainability section assesses the degree and potential to which project interventions or impacts will continue once the project ends and what mechanisms are in place to ensure the sustainability.

- In what way did the project involve local authorities, government or other stakeholders through any commitment or support towards achieving the project? What is the expected/planned degree of local/state support for continuation of the started interventions? - What measures or mechanisms have been implemented by the partner to ensure the sustainability of the project outcomes? - What is the likelihood that achievements in the various outputs/outcome are being sustained beyond the project period? - What more must be done to ensure / retain the changes and momentum generated will continue beyond the project period?

Disability Inclusion and Gender Equality: The evaluation must consider gender and inclusion aspects of the project and report on this. Data collected must be disaggregated according to gender, age and disability status.

- How have persons with disabilities and their organisations been involved in planning and implementing the project? What more could have been done to increase their involvement in implementation? - How was the equal participation of girls and boys, women and men, persons with disabilities as well as marginalized communities ensured? What is the ratio of women and men in the project? What is the ratio of women and men with disabilities? Does this adequately reflect the ratio of males and females with disability in the target region? Is the focus on the caregivers appropriate? Does the project reinforce unequal duties such as for example taking care of children with disabilities? - To what extent is the project inclusive of refugees? Were refugees considered in the project’s design, implementation, and evaluation phases? If yes, how? - Are project activities, services, and communications accessible and relevant to both host communities and refugees? What measures were taken to allow accessible communication with persons with disabilities during implementation?

Safeguarding of children and adults at risk

- What measures were already in place or put in place during implementation to ensure safeguarding of children and adults at risk? - Have any trainings been conducted to increase awareness in communities, at administrations, schools and other engaged entities? - Was an accessible feedback mechanism in place? Are people aware of its existence and use?

## Methodology

The detailed methodology shall be developed by the evaluation team in close consultation with the project partners and CBM. A first outline of the proposed methodology shall be provided in the Expression of Interest /Consultancy Offer. The evaluation shall be results based (outcome and impact) rather than activities based. It shall be a participatory and inclusive process conducted by involving the implementing partner, stakeholders, and representatives from the target group. Particular attention shall be given to people with disabilities and/or their families in terms of their involvement in the evaluation and accessibility of its results. Therefore, sampling should deliberately include persons with disabilities and/or their families from the target group. The evaluation shall involve female and male adults and children with disabilities and their families, including refugees, that are affected by the project. Necessary accommodations in the methodology (sign language, accessible venues, additional time) must be made to ensure inclusion.  The following mechanisms must be adhered to during the entire process:

- Participatory and inclusive

- Safeguarding of children and adults at risk

- Data Disaggregation (gender/age/disability)

- Data Security and privacy (data storage and informed consent)

It is suggested to use mixed methods incl. qualitative and quantitative methods. This will likely include, at a minimum:

- Document and systems review:  Review of existing documentation, including; project plan and reports, project log frame, and monitoring and evaluation data.

- Surveys: Application of structured survey questionnaires with a representative, random sample of the target population to quantitatively assess outcomes. This will be greater in scope, breadth, and depth compared to standard routine project monitoring.

- Focus Group Discussions with target groups and other stakeholders to assess implementation experiences and effectiveness, document successes, challenges and lessons learned and develop recommendations for improvement.

- Key Informant Interviews: Consultations with key project stakeholders, including field staff and partners.

- Collection of personal stories that allow to illustrate the changes in the life of some individuals as a result of the interventions.

The evaluation shall be conducted using rights-based principles, i.e. be participatory, inclusive and following a do-no-harm approach. Data security and privacy issues must be adhered to during data collection, management as well as reporting. The project team will share a matrix of key partners and stakeholder with the evaluator so that s/he is aware on who to include in the sampling.

## Management Responsibilities and Evaluation Team

Commissioning responsibility

The evaluation will be under the responsibility of the CBM Eastern Mediterranean Programme. The local implementing partner KHF will be involved in drafting the Terms of Reference, reviewing and providing input to the final report.

Responsibility of CBM Eastern Mediterranean Programme includes:

- Tendering of Evaluation Team/ Consultancy Company

- Facilitate the initial evaluation briefing and the post –review session

- Communicate with the consultant/evaluation team leader on any significant issues arising before and during the evaluation.

- Review and approval of detailed methodology and work plan

- Review and approval of final evaluation report and recommendations according to the reporting template provided by CBM.

- Conclusion of Contract with Evaluation Team

- Arrangement of Payments to Evaluation Team

- Complete process and report finalisation.

KHF has the responsibility to make sure that relevant stakeholders are aligned and available for discussions as well as provide their feedback to the draft evaluation report. Furthermore, the evaluation will be kicked off with a briefing of the partner organisations CBM and KHF and the Evaluation Team. A final wrap-up meeting/workshop shall be conducted by the same parties, with the format and location to be determined at a later stage.

The Evaluation Team plays a central role in generating evidence-based insights that promote reflection, learning, and improvement. Their responsibilities include:

- Reviewing and analysing the overall project implementation against planned objectives, activities, and indicators.

- Identifying lessons learned and providing practical, actionable recommendations for future programming.

- Ensuring accessibility of findings through a clear and user-friendly final report that can serve as a reference for all stakeholders.

- Facilitating feedback collection, particularly from persons with disabilities, to ensure participatory input that informs future project design and delivery.

- Highlighting what worked well and what needs improvements in the future projects supporting informed decision-making.

In terms of logistics, the evaluation team is responsible for:

- Arranging (international) travel details and making sure to have a relevant visa if required. CBM and KHF can support in obtaining invitation letters.

- Arranging accommodation, having relevant insurances and monitor the safety and security situation for any travel.

- Ensuring appropriate translation or interpretation is covered as needed, including potential provision of sign language interpretation.

KHF shall recommend accommodation options and will arrange meetings and local logistics in close alignment with the Evaluation Team. KHF shall make sure that venues are accessible for persons with disabilities.

CBM and KHF can support logistical arrangements as needed.

The recommendations of the evaluation shall be used to draft a Management Response (template to be provided through CBM for further action).

Requirements of the Evaluation Team

The consultant/evaluation team applying for this evaluation shall have the following qualifications:

- Master’s degree or higher academic degree related to community based inclusive development/community-based rehabilitation/rights of persons with disabilities, or similar

- Technical expertise in CBID and/or CBR, disability and inclusion

- Proven working experience with NGOs and INGO and the government sector in the field of community based inclusive development/rights promotion

- Proven consultancy experience of at least 5 years with a record of providing high quality, expert advice

- Proven experience in the evaluation of projects/programmes by BMZ or similar institutional, DFAD, DFID.

- Experience in evaluation of similar programmes and sound knowledge of (inclusive) Project Cycle Management (iPCM)

- Experience in participatory approach is a must as well as facilitation skills

- Excellent analytical skills

- Proven working experience in the field of inclusion, disability and gender mainstreaming

- Knowledge about local culture, policies and laws to understand the reality for persons with disabilities in the country

- Excellent English report writing skills, ability to write in a structured and concise manner

- Proactivity and persistence will be required

- Proficiency in written and spoken Arabic and English is a must

- Ideally, the evaluation team shall include a mixed gender team and be inclusive of a person with disability.

The evaluation team is expected to be medically insured during the time of service under this consultancy. The contracting agency will not take responsibility for any damage, injury, or loss in the framework of this evaluation. Verification of these qualifications will be based on the provided curriculum vitae. Moreover, references, web links or electronic copies of two or three examples of recently completed evaluation reports shall be provided together with the technical proposal.

Candidates are also encouraged to submit other references such as research papers or articles that demonstrate their familiarity with the subject under review.

CBM Children and Adults at Risk Safeguarding Policy: As a condition of entering into a consultancy agreement the evaluators must sign the CBM Code of Conduct and the Safeguarding Policy and abide by the terms and conditions thereof.

## Deliverables

The End-Term evaluation is expected to start in November 2025 with an inception phase followed by data collection (desk review, interviews, and surveys), analysis, and report writing. A workshop for presentation and discussion of preliminary findings, and the final revised evaluation report should be delivered no later than end of December 2025 (exact dates will be agreed on later).

- The Consultant will provide an evaluation plan with a detailed methodology to the CBM.

- The Consultant will take part in a briefing on the basis of the evaluation plan and detailed methodology with KHF and CBM.

- There will be a feedback session with the main team/staff from the implementing partner on the main findings and recommendations.

- The Consultant will prepare a Comprehensive Evaluation Report for submission to CBM by end of December 2025 taking into consideration inputs from all key stakeholders in the prescribed format/template detailed as requested and provided by CBM (inclusive of an executive summary). The final report shall include lessons learned and recommendations to the project team and CBM.

- All background material shall be delivered, incl. (anonymised) questionnaires, (anonymised) surveys, consent forms, etc. in the form of an Annex.

Evaluation Plan and detailed methodology due by: Two weeks after start of assignment

Draft Report due by: Two weeks after the visit to project sites

Finalised Report due by: Three weeks after submission of draft evaluation report

## Evaluation Schedule

The consultant will provide the following deliverables to the CBM and KHF team within the timeframe stated:

Inception Report: within 4 working days of evaluation launch, a detailed report on the evaluator’s proposed approach to the evaluation will be submitted for approval. This will provide a detailed description of the methodology and tools, research questions, analytical methods, , and detailed work plan, incl team member responsibilities for the entire exercise. Draft questionnaires and interview forms will also be submitted for review at this stage.

Data collection: testing questionnaires, refining data collection tools, and administering data collection within 12 working days of the evaluation launch.

Data analysis and reporting: The consultant will present the preliminary findings for discussion with KHF and CBM. This should include a draft set of findings and analysis.

Final Report: should be no longer than 30 pages – excluding the executive summary and annexes, to the point, and written in plain English. The report must explain the purpose of the evaluation, exactly what was evaluated, and the methods used (with their limitations). The report will present evidence-based and balanced findings, consequent conclusions, lessons, and recommendations, which will be cross-referenced to each other. The report should be presented in a way that makes the information accessible and comprehensible. Any dissident views in response to evaluation findings will be appended in a footnote or annex as appropriate. To avoid repetitions in the report, the authors will use numbered paragraphs and make cross-references where possible.

The following table provides a roughly expected time frame:

| Task | Location | Number of Days | Expected Dates |
| --- | --- | --- | --- |
| Briefing | Online | 1 day | tbd |
| Desk Study | Consultants’ desk | 4 days |  |
| Field Phase, Project Visit or remote data collection phase | … KHF/IFH HQ, East Amman Community centre | 6 days |  |
| De-briefing with initial findings | Online | 1 day |  |
| Analysis and draft report | Consultants’ desk | 4 days |  |
| Finalising report | Consultants’ desk | 3 |  |
| (Option of wrap-up workshop with stakeholders) | Online/partner or CBM office | 1 |  |
| TOTAL |  | 20 working days |  |

## Payment Mode

Once the consultancy/evaluation contract is signed, the payment will be arranged in three instalments. The first instalment of 25% will be made upon signing the contract. A second instalment of 25% will be paid after submission of the draft report. The remaining balance will be paid to the evaluator upon clearance of the final report by CBM. All payments can only be processed based on an invoice, including an overview of payments and supported by receipts of all expenditures and time sheets.

## Applications

Expressions of Interest shall be submitted by (October 15, 2025) to (info.em@cbm.org) and shall include:

- Brief description of consultancy firm/consultant/team

- Detailed CVs of the team lead and/or each of the suggested team member

- Technical proposal and suggested methodology

- Availability of team and suggested schedule

- Financial proposal

- A reference list of three previous customers

The financial proposal of consultant costs should include the following:

- Fees, incl. taxes

- Accommodation, transport, meals, (will be reimbursed against original receipt)

- Costs during evaluation, such as refreshment during interviews and rental of venues (will be reimbursed against original receipt)

Only complete applications will be considered. The contractor may ask for references and/or examples of previous work and reports during the recruitment process. The contractor reserves the right to terminate the contract in case the suggested and agreed upon team members are unavailable at the start of the evaluation and no adequate replacement can be provided.

## Documents

Documents such as project description, logical framework or theory of change documents, most recent reports, recent financial report, any previous assessment, review, evaluation report (as applicable) will be provided to the evaluation team. Note that those documents will be made available to the consultant after signature of contract.