TERMS OF REFERENCE AUDIT

CBM Project No. P10439-BMZ-MYP

Project Title:

Strengthening the resilience of refugees and host communities in Jordan focusing on women affected by GBV

Reporting Entity:

King Hussein Founadation

Contracting Authority:

CBM Country Office Eastern Mediterranean

CONTENT

1.	Introduction	1

2.	About the Project	2

3.	Background and Objective	2

4.	Standard and Ethics	3

5.	Qualifications of the Auditor	3

6.	Duties of the Reporting Entity	3

7.	Task of the Auditor	4

8.	Audit Report	5

9.	Timeframe	6

10.	Annexes	7

# Introduction

The present document and the annexes listed in section 10 are the terms of reference (‘ToR’) on which CBM Country Office Eastern Mediterranean (hereafter named Contracting Authority) agrees to engage ‘the Auditor’ to perform an audit of the funds received and payments made by the Reporting Entity King Hussein Foundation (KHF) incurred under the BMZ financed contract on the cover sheet. These ToR will become an integral part of the contract concluded between the Contracting Authority and the Auditor.

# About the Project

| Project #: | P10439 |  |
| --- | --- | --- |
| Title: | Strengthening the resilience of refugees and host communities in Jordan focusing on women affected by GBV |  |
| Period: | 01.09.2024 - 31.12.2028 |  |
| Location: | Jordan (East Amman, Irbid, Alkarak) |  |
| Implementing Partner: | King Hussein Foundation |  |
| Objectives: | In the governorates of East Amman, Irbid, and Karak, people with disabilities, women, and girls face limited access to essential health and education services, combined by the absence of comprehensive rehabilitation programs. These issues are further exacerbated by limited community awareness, as many health and education professionals lack sufficient knowledge about disability, inclusion, rehabilitation, and gender-based violence (GBV). Furthermore, women and girls are not adequately organized in self-help structures, and many lack the awareness and tools to protect themselves from GBV. Meanwhile, vulnerable youth, including refugees and people with disabilities, continue to face barriers to employment and entrepreneurship opportunities, limiting their abilities to achieve financial independence and social inclusion. To address these gaps, the project aims to improve the living conditions of refugees and host communities by enhancing access to inclusive health, education, and rehabilitation services in line with the principle of "Leave no one behind"; establishing peer support networks for women and girls affected by or at risk of GBV, raising awareness on GBV and inclusion across the broader community; and strengthening the economic resilience of vulnerable groups through support for income-generating activities and small business development. |  |
| Budget (Implementing Partner): | Period | Budget |
|  | 01.09.2024 - 31.12.2024 | 119,628 EUR |
|  | 01.01.2025 - 31.12.2025 | 528,802 EUR |
|  | 01.01.2026 - 31.12.2026 | 581,053 EUR |
|  | 01.01.2027 - 31.12.2027 | 645,192 EUR |
|  | 01.01.2028 - 31.12.2028 | 386,934 EUR |
| Donors: | BMZ |  |

# Background and Objective

The Reporting Entity has received funds from CBM Christoffel-Blindenmission Christian Blind Mission e.V. to implement the project named on the coversheet of these ToR. The funds transferred by CBM to the Reporting Entity are co-financed by the German Ministry of Economic Development and Cooperation (BMZ). Therefore, the funds need to be disbursed in accordance with BMZ rules and regulations. The Ministry is informed annually about the funds the Reporting Entity received from CBM and the disbursement of these funds.

The objective of this audit is:

-to express an opinion on the project financial statement for the following reporting period:

Annual audits for the years 2024 (01 September – 31 December) 2025, 2026, 2027 and 2028.

- to issue reports as stipulated in Section 8

# Standard and Ethics

The Auditor shall undertake this engagement in accordance with the International Federation of Accountants (IFAC) Code of Ethics for Professional Accountants, developed and issued by IFAC’s International Ethics Standards Board for Accountants (IESBA), which establishes fundamental ethical principles for Auditors about integrity, objectivity, independence, professional competence and due care, confidentiality, professional behaviour, and technical standards.

The Contracting Authority requires that the Auditor be independent from the Reporting Entity and complies with the independence requirements of the IFAC Code of Ethics for Professional Accountants.

# Qualifications of the Auditor

General requirements

By agreeing these ToR, the Auditor confirms meeting at least one of the following conditions and provides written proof:

- The Auditor is a member of a national/international accounting or auditing body or institution which in turn is a member of the International Federation of Accountants (IFAC).

- The Auditor is a member of a national/international accounting or auditing body or institution. Although this organisation is not member of the IFAC, the Auditor commits to undertake this expenditure audit in accordance with the IFAC standards and ethics.

The Contracting Authority is obliged to prove the qualification of the Auditor to BMZ by a confirmation of the German Embassy or a recognised national/international institution (e.g. Chamber of Commerce or official Association of Auditors).

Qualifications

The Auditor has appropriate professional qualifications and suitable experience with IFAC standards and with experience in verifying financial information of projects comparable in size and complexity to the project subject to this audit. In addition, the Auditor should

- have experience with projects related to development cooperation funded by national and/or international donors and institutions.

- hold a relevant university degree or professional qualification. He should have at least 6 years of experience as a professional Auditor or accountant in public audit practice including relevant managerial experience of leading audit teams.

# Duties of the Reporting Entity

The duties of the Reporting Entity include the following:

- To prepare the project accounting, annual and final financial statement (Template of Annual Financial Statement see Annex 1 and Final Financial Statement see Annex 2) with the voucher lists and all related project documentation in time so that the audit can take place.

- To provide the Auditor with the annual and final financial statements and voucher lists which have been prechecked by the Contracting Authority for the preparation of the audit.

- To provide access to all legal documents, correspondence, bank statements and any other information associated with the project during the auditing period. This includes the following documents:

  - Project Full Proposal

  - Project Contract with approved Budget

  - Revised Budgets (if any)

  - BMZ-Guidelines for the funding of projects incl. special provisions

  - BMZ-Guidelines for external Audits

  - All project-related vouchers (for income, expenditures, transfers, currency exchange, etc.)

  - All project-related contracts (staff and consultant contracts, rent contracts, contracts with constructors etc.

  - All project-related procurement documents including procurement award notices.

  - All further project-related documents necessary for the auditor

- To coordinate the Auditors field, visit to ensure that he can inspect all equipment/activities agreed during the preparatory meeting:

- To provide a management response to the Auditor’s observations that were made during the audit within the given timeframe stipulated in Section 8

# Task of the Auditor

The audit shall be conducted at the project location, particularly where the project bookkeeping is done. The auditor’s assignment includes the following tasks:

- To examine whether all project funds have been used in accordance with the conditions stipulated in the project documents listed above under 5. c. 1. – 4. with due attention to principles of economy and efficiency, and only for purposes for which financing was granted.

- To examine whether internal administrative and financial control measures are adequate and compliant with local laws and donor’s requirements as stipulated in the documents listed under 5.c. 1-4.

- To examine whether the project accounts have been prepared in accordance with consistently applied International Accounting Standards and whether they give a true and fair view of the financial situation of the project and its resources and expenditures.

- To examine the bank account opened specifically for the project and any further bank accounts on which the project funds are administered.

- To examine whether the project bookkeeping accounts with all vouchers, supporting documents, records and accounts have been properly kept and correctly filed on cash book basis. It is expected that the auditor examines 100% of all supporting documents.

- To examine whether expenditures are correctly booked in conformity with BMZ budget lines of the BMZ-financing plan, and all vouchers are clearly stamped with the project number.

- To examine whether the expenditures documented by vouchers are identical to the annual expenditures reported in the voucher lists.

- To examine whether goods and services financed by the project have been procured in accordance with the relevant procurement guidelines as stipulated in the in the documents listed under 5.c. 1-4.

- To examine whether contracts of project staff financed by the project are in accordance with national law with regard to social security payment and taxation and whether part-time work is recorded with correctly filled timesheets.

- To examine whether the inventory list is complete and correctly filled.

- In case of final audits, to examine whether over- or underspending of more than 30% in comparison to the financing plan have occurred and to examine the reasons for the deviations.

- To carry out a physical inspection of the project location, equipment procured, and activities as agreed during the preparatory meeting.

# Audit Report

The Report Audit report shall include the following:

- For annual audits, a financial statement in the currency in which the expenditure occurred, according to the format provided in Annex 1.

For final audits, a cumulated financial statement in the currency in which the expenditures occurred, according to the format provided in Annex 2.

In both cases, annual and end of project audit, the financial statement shall include any income received by the project, any interests received on the project bank account as well as all project expenditures during the auditing period.

Each financial statement shall contain notes providing details as deemed necessary by the Auditor.

- Complete voucher lists signed and certified by the Auditor.

- A stamped and signed inventory list.

- An Auditor's certificate which shall contain the following:

We hereby certify that we have audited the Financial Statement of (LUPD) with reference to the financing of the project (Enhancing food security and strengthening socio-economic resilience in crisis on community-level in Bekaa Valley, Mount Lebanon and South Lebanon) on the basis of the following documents made available to us (please list the documents). To this end, we have inspected the books and vouchers and report that:

(1) Income and expenditure are properly proved in the form of vouchers.

(2) The proved expenditures are in line with the appointed purpose as set out in the Annex 1 of the Tripartite Contract. In case of final audits: Any deviations from the Financing Plan of more than 30% are described and explained separately.

(3) The amount and origin of documented income which is accounted for as counterpart contributions made by CBM, the executing agency, the target group and/or other agencies in the project country have been specified.

(4) The conditions for project implementation set by the donor have been observed/have not been observed in the following points.

(5) Any particularities which need to be mentioned.

In the certificate the Auditor shall make explicit and concrete statements on each of the areas examined (see point 6.) and audit findings identified. Even if in any of the areas no audit findings were identified, the Auditor shall make a statement on this fact.

- In addition to the audit report, the Auditor will prepare a management letter including the following:

  - Identified deficiencies and areas of weakness in the financial systems and controls and recommendations for improvement as well as comments and observations on the accounting records that were examined during the audit.

The report shall also include the management response of the reporting entity for each observation raised by the Auditor. Any following audit shall verify whether the recommendation was implemented by the reporting entity.

  - A report on the degree of the reporting entity compliance with the financing conditions contained in the Annexes, and comments – if any – on the internal and external matters affecting such compliance.

  - Matters that have come to attention during the audit which might have a significant impact on the implementation of the project.

# Timeframe

Preparatory Meeting and start of the audit.

The Contracting Authority foresees a preparatory meeting with the Auditor at the official start for the project held virtually.

After three months of project implementation, the Auditor will undertake a half-day preliminary examination of the bookkeeping at the Reporting Entity and shall provide the Reporting Entity with recommendations.

The annual audits with the reporting period 1st January-31st December (exception for the first report: 1 September 2024 – 31 December 2025) shall start as soon as the annual financial statement of the project is completed by the Reporting Entity, but under no circumstances later than six weeks after the end of the reporting period.

The final audit for the overall implementation period of the project shall start at the latest two months after the project ended.

Timeframe for audit reports

The Auditor will submit a draft report to the Reporting Entity (with copy to the Contracting Authority) within 15 calendar days after the start of the audit and ask for its comments to be received within 5 calendar days.

5 calendar days after receiving the Reporting Entity's comments, the Auditor will submit a pre-final report to the Contracting Authority for comment and approval. Should it not be possible for the Auditor to meet this deadline due to exceptional circumstances, the auditor shall ask the Contracting Authority for approval to extend the deadline. The Contracting Authority may request the Auditor to carry out additional work, in which case a reporting deadline should be agreed on a case-by-case basis.

5 calendar days after receiving the Contracting Authority's comments, the Auditor will submit the final report for the Contracting Authority's approval. Should it not be possible for the Auditor to meet this deadline due to exceptional circumstances, the auditor shall ask the Contracting Authority for approval to extend the deadline.

Once the audit report is approved by the Contracting Authority, the Auditor shall send a scanned copy of the signed and stamped Financial Statement within 3 calendar days to the Contracting Authority by email. The Auditor will provide 3 printed originals of the audit report (in case of final audit 4 printed originals) to the Contracting Authority latest 7 calendar days after the audit report was officially approved.

# Annexes

- Financial Statement Template for Annual Audits

- Financial Statement Template for Final Audits

###### Annex1: Template Statement of application of funds for annual audits (Quantitative documentary proof)

Project number

Statement of accounts for    20     to   20       [Please fill period]

Financial statement as at           [Please fill date]

| 1 |  | Expenditure |  | Actual expenditure during reporting period |
| --- | --- | --- | --- | --- |
|  |  |  |  | in local currency |
| 1.1 |  | for investments |  |  |
| 1.1.1. |  |  |  |  |
| 1.1.2 |  |  |  |  |
| 1.1.3 |  |  |  |  |
| 1.1.4 |  |  |  |  |
| 1.2 |  | for operating expenditure |  |  |
| 1.2.1 |  |  |  |  |
| 1.2.2 |  |  |  |  |
| 1.2.3 |  |  |  |  |
| 1.2.4 |  |  |  |  |
| 1.3 |  | for personnel |  |  |
| 1.3.1 |  |  |  |  |
| 1.3.2 |  |  |  |  |
| 1.3.3 |  |  |  |  |
| 1.3.4 |  |  |  |  |
| 1.4 |  | for evaluation or study |  |  |
|  |  | Project expenditure |  |  |
|  |  | Total expenditure |  |  |
| 2. | Receipts |  | Actual receipts during reporting period |  |
|  |  |  | – in local currency – |  |
| 2.1 | BMZ grant and financial contribution from private executing organisation |  |  |  |
| 2.2 | Contribution from project-executing agency, target group and/or other source in developing country |  |  |  |
| 2.3 | Additional resources (e.g. interest, sales revenue) |  |  |  |
|  | Total receipts |  |  |  |

| 3. | Financial statement as at |  |  |  |
| --- | --- | --- | --- | --- |
|  |  |  |  | – in local currency – |
|  | Balance from previous year |  |  |  |
|  | Total receipts current year |  |  |  |
|  | Total receipts current year plus balance from previous year (=total available funds) |  |  |  |
|  | Total expenditure |  |  |  |
|  | Balance |  |  |  |

It is confirmed that no funds were available for the financing of the project other than the receipts detailed above. It is also confirmed that all expenditure was necessary, that funds were utilized efficiently and economically and that the information given conforms with the books and vouchers.

(Place)	(Date)

(Signature and stamp)

###### Annex2: Template: Statement of application of Final Accumulated audit (All Years) (Quantitative documentary proof)

Project number

Statement of accounts for    20     to   20       [Please fill period]

Financial statement as at           [Please fill date]

| 1 | Expenditure | Total appropriation according to Financing Plan of [date] | Actual expenditure 20 to 20 (first year) | Actual expenditure 20 to 20 (second year) | Actual expenditure 20 to 20 (third year) | Actual expenditure 20 to 20 (fourth year) | Actual expenditure ALL YEARS accumulated | Deviation (Actual total expenditure versus total appropriation) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | in local currency | in local currency | in local currency | in local currency | in local currency | in local currency | – as a % – |
| 1.1 | for investments |  |  |  |  |  |  |  |
| 1.1.1. |  |  |  |  |  |  |  |  |
| 1.1.2 |  |  |  |  |  |  |  |  |
| 1.1.3 |  |  |  |  |  |  |  |  |
| 1.1.4 |  |  |  |  |  |  |  |  |
| 1.2 | for operating expenditure |  |  |  |  |  |  |  |
| 1.2.1 |  |  |  |  |  |  |  |  |
| 1.2.2 |  |  |  |  |  |  |  |  |
| 1.2.3 |  |  |  |  |  |  |  |  |
| 1.2.4 |  |  |  |  |  |  |  |  |
| 1.3 | for personnel |  |  |  |  |  |  |  |
| 1.3.1 |  |  |  |  |  |  |  |  |
| 1.3.2 |  |  |  |  |  |  |  |  |
| 1.3.3 |  |  |  |  |  |  |  |  |
| 1.3.4 |  |  |  |  |  |  |  |  |
| 1.5 | for evaluation or study |  |  |  |  |  |  |  |
|  | Total |  |  |  |  |  |  |  |
| 1.6 | Reserve funds (appropriations only) |  | ——— | ——— | ——— | ——— | ——— |  |
|  | Total |  |  |  |  |  |  |  |

| 2. | Receipts | Budgeted receipts according to Financing Plan of [date] | Actual receipts 20 to 20 (first year) | Actual receipts 20 to 20 (second year) | Actual receipts 20 to 20 (third year) | Actual receipts 20 to 20 (fourth year) | Actual receipts ALL YEARS accumulated | Deviation (Actual total receipts versus total appropriation) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | – in local currency | in local currency | in local currency | in local currency | in local currency | in local currency | – as a % – |
| 2.1 | BMZ grant and financial contribution from private executing organisation |  |  |  |  |  |  |  |
| 2.2 | Contribution from project-executing agency, target group and/or other source in developing country |  |  |  |  |  |  |  |
| 2.3 | Additional resources (e.g. interest, sales revenue) |  |  |  |  |  |  |  |
|  | Total receipts |  |  |  |  |  |  |  |

| 3. | Financial statement as at |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | – in local currency – |  |
|  | Total receipts (all years) |  |  |  |  |
|  | Total expenditure (all years) |  | ./. |  |  |
|  | Balance |  |  |  |  |
|  | Overspending |  |  |  |  |

It is confirmed that no funds were available for the financing of the project other than the receipts detailed above. It is also confirmed that all expenditure was necessary, that funds were utilized efficiently and economically and that the information given conforms with the books and vouchers.

(Place)	(Date)

(Signature and stamp)

Please note that for final audits several particularities apply (in each case highlighted cursive and bold)

Overspending = Actual total expenditure – Appropriation total expenditure according to Financing Plan