Terms of Reference for Consultancy
Situation Analysis and Country Plan Development
for the CBM Eastern Mediterranean Program

ABOUT CBM
Christoffel-Blindenmission Christian Blind Mission e.V. (CBM) is an organization working internationally for development and humanitarian aid. Based on Christian values, it works to improve the lives of people with disabilities who live in the poorest regions of the world. CBM not only provides medical aid and enables prevention and rehabilitation, but it also works towards a comprehensive realization of human rights and the full social participation of people with disabilities. This includes opportunities for education and employment. With its political work, CBM seeks to achieve that the rights of people with disabilities are considered in development and humanitarian policies – and that this is also financed.

CBM is responsible for program work in developing countries financed by donors and carried out by local implementing partner organizations. CBM adds value by bundling powers and resources of people and institutions with the same kind of interests. Moreover, CBM contributes its expert knowledge acquired over many years to issues involving development/humanitarian aid and disabilities. It therefore supplements and strengthens the commitment of its supporters. CBM follows the vision of an inclusive world in which all persons with disabilities enjoy their human rights and achieve their full potential.

The goal of CBM is to become a leading organization in disability-inclusion, development and humanitarian aid. We concentrate on the fields of community-based inclusive development (CBID), inclusive health (IH) and inclusive humanitarian action (IHA). The humanitarian work of CBM is based on the four humanitarian principles (humanity, neutrality, impartiality, and independence), as well as relevant internal and international standards and guidelines.

About Eastern Mediterranean Programme:
CBM has been working in the Eastern Mediterranean region for over 54 years. First commencing operations in Egypt in 1968, we then furthered our programmatic work to the Occupied Palestinian Territories (OPT) and Yemen in 1975, Lebanon in 1980, and Jordan in 1987. As part of CBM's decision to be close to the field, CBM International decided in 2024 to open an office in Jordan that currently supports partners in OPT, Jordan, and Lebanon.

Working alongside local partners and local governments, CBM in the Eastern Mediterranean region has been partnering with organizations to deliver services that improve inclusive health, education, disability-inclusive disaster risk reduction, and livelihoods for persons with disabilities and those at risk of disabilities. CBM is promoting disability-inclusion in policies and practices moving from persons with disabilities as only being beneficiaries of services to actors in their own lives as rights holders. CBM in the Eastern Mediterranean Region has been partnering with organisations to serve and support persons with disabilities, to promote and implement an approach of disability-inclusive development that is grounded in human rights, and to achieve and promote compliance with the Convention on the Rights of Persons with Disabilities (CRPD).

The country plan for the Eastern Mediterranean region shall be aligned with CBM’s vision, mission and CBM’s 2030 strategy. The Eastern Mediterranean Programme will expand its scope of activities in certain technical areas which are not completely new, i.e., Inclusive Humanitarian Action (IHA), Community Support Services, and Systems (CSS), Social Protection, and Institutional Fundraising. With this approach, CBM wants to maximize impact for persons with disabilities in the region.

Situation Analysis and Facilitation of Country Plan Development

Purpose:
To conduct a high-level situation analysis and facilitate the development of a 5-year Country Plan (CP) for CBM in close collaboration with CBM’s Eastern Mediterranean Program (EMP), with a focus on identifying critical needs, gaps, and opportunities in Jordan, Lebanon, and Palestine.  The CP shall be aligned with CBM’s Strategy 2030 to support systemic, long-term change and inclusive development for persons with disabilities. CBM is seeking to commission a consultant to support EMP with addressing the following key elements:

- Facilitate a workshop with CBM’s EMP team to develop the strategic objectives of CBM’s EMP for a 5-year timeframe and consolidate the results as part of a draft country plan.

- Analyse the context and situation in the region and assess what resources including existing and potential donors, partnerships, and strengths EMP currently possesses to achieve the objectives developed in the workshop.

- Identify any gaps between current resources and those required to achieve the objectives.

- Support EMP to develop actionable recommendations and strategies based on SMART indicators to address the identified gaps and strengthen CBM’s approach to disability-inclusive development in the region.

Scope of Work:
The consultant will deliver the following components to support EMP in achieving a comprehensive understanding of the needs and resources, and, collaboratively with EMP, develop ideas that advance the EMP portfolio and create a sustainable impact:

- High-Level Situation Analysis:
A detailed situation analysis shall be conducted in Jordan, Palestine and Lebanon to better understand current conditions, risks and specific challenges and barriers that persons – particularly women and girls – with disabilities face and to identify critical needs, gaps, and opportunities for CBM and its partners.

Key Areas of Focus:

  - Security and Safeguarding Risks: Provide a) a brief history and overview of conflict crime and natural disasters in the region, b) a short note to medical risks – also for visitors – and how the EMP team handles them, c) a statement on possible communal tensions between social or religious groups and underlying reasons, d) references to protocols in place to keep staff and visitors safe, e) hints to more dangerous areas (cities, parts of a country) and underlying reasons.

  - Implementation of Disability-Inclusion: Assess the general context and the status of implementing inclusion for persons with disabilities, including progress on SDGs and CRPD implementation, identify shadow reports from civil society in case of availability as well as advocacy initiatives.

  - Identify common intersectional protection risks and gaps needing attention.

  - Humanitarian Needs and Disaster Preparedness: Analyse the humanitarian landscape and identify needs and potentials for disability-inclusive humanitarian aid and disaster risk reduction (DRR).

Output: A comprehensive situation and context analysis that includes tangible recommendations.

- Partner and Project Portfolio Review:

- Conduct a SWOT analysis of the current CBM partner portfolio in EMP to identify challenges, opportunities, lessons learned, and gaps and propose opportunities for improvement, considering particularly the needs of persons with disabilities.

- Based on the findings of the SWOT analysis, recommend potential new suitable partners for collaboration to diversify the partner portfolio.

Projects of potential new partners could:

- Mainstream MHPSS and Psychological First Aid (PFA) (disaster risk mitigation projects)

- Include protection planning, inclusive evacuation plans, building-back-better measures (humanitarian projects)

- Focus on livelihood opportunities (development projects: TVET, employment opportunities, MSME development; humanitarian aid projects: cash-for-work)

- Align efforts with the Humanitarian-Development-Peace (HDP) nexus and social cohesion

- Identify areas where partners can collaborate or strengthen each other’s efforts.

Output: An updated partner portfolio mapping with recommendations for developing existing and new partnerships that have the potential to enhance the impact of EMP.

- Stakeholder Analysis

- Map relevant local stakeholders, including OPDs, international donors, government institutions, clusters, working groups and development networks that could, contribute to partner collaboration and strengthening CBM’s work in the region, identify common goals of those stakeholders with CBM’s, and gaps in current stakeholder collaboration, and recommend additional stakeholders relevant for further in-depth collaboration.

- Develop strategies for engaging those stakeholders, including OPDs and government entities, and integrating their perspectives into CBM’s initiatives.

Output: A summary of the stakeholder analysis, including insights from stakeholder consultations and recommendations how to improve CBM’s visibility and coordination with key stakeholders that have a similar vison like CBM.

- Workshop with EMP to develop a draft of the regional plan:

- Based on the situation analysis, partner portfolio review, and stakeholder analysis, the consultant shall facilitate a workshop supporting the EMP team to develop a 5-year strategic plan for the region, aligned with CBM’s Strategy 2030, regional plan, fundraising strategies, the CBM Advocacy Plan 2030, the SDGs and national development plans and initiatives. The EMP strategic plan developed with facilitation of the consultant aims for a holistic, systemic change and shall include lessons learned from current implementations and input from the various stakeholders.

- Record and consolidate the results of the workshop with EMP contributing to the draft EMP country plan.

- Outline proposed actions and strategic priorities to address identified gaps and optimize program impact.

Methodology:

- Desk Research: Review updated and relevant documents, reports, previous situation analyses, and needs analysis reports, on protection, health, education, livelihood, MHPSS, humanitarian action, disability-inclusion, Community-Based Inclusive Development (CBID), DRR, and disability-specific policies, laws, and other legal instruments.

- Interviews and Focus Group Discussions: Conduct key informant interviews with 17 existing or potential partner organisations and with 12 other stakeholders (4 per country) including OPDs, INGOs and government entities as well as 12 focus group discussions (4 per country) with existing and potential partners to validate findings and enrich the analysis with practical insights.

Stakeholder Consultations: Facilitate meetings to gather qualitative data on experiences, needs, and suggestions from various stakeholders.

Expected Outcomes:
The completed deliverables will provide CBM with:

- A clear understanding of opportunities, needs, and gaps to increase funding opportunities in the region.

- A consolidated strategic roadmap and well-structured draft strategic plan for EMP as a result of the workshop facilitated for the EMP team, aligned with CBM’s vision, adapted to the unique challenges and opportunities in the region and addressing identified needs to strengthen partnerships and expand CBM’s impact.

GUIDANCE NOTES ON FINAL DELIVERABLES:

- A power point presentation to be presented to the EMP team (before the workshop) covering the initial findings of the situation analysis, partner portfolio review and stakeholder analysis as well as initial recommendations including associated risks.

- The EMP strategic plan draft to be provided in the defined format including recommendation of actions and not exceeding 15 pages based on the outcomes of the workshop facilitated for the EMP team and starting with a 2-page summary outlining the high-level key findings of the situation analysis, the partner portfolio review as well as the stakeholder analysis. After integration of feedback from CBM a final version of the country plan is to be submitted.

- An annex to be provided which comprises all data collected during the situation analysis, partner portfolio review and stakeholder analysis as well as other supporting documents.

Timeline:
The consultancy is expected to be completed within 40 working days with regular check-ins and drafts submitted at key milestones.

Qualifications of the consultant:

- Proven previous experience in conducting situation or context analyses considering partner and project portfolios of international NGOs and supporting the development of strategic country plans for international humanitarian or development NGOs or relevant fields.

- Knowledge of the Middle Eastern Region.

- Proven knowledge of focus group discussions, individual interviews and SWOT analyses as well as participative tools.

- Prior experience in working with INGOs and local NGOs.

- Good communication skills.

- Knowledge in Community-Based Inclusive Development and inclusion policies is an asset.

- Insight into challenges that persons with disabilities face.

- Knowledge in Humanitarian response and action.

- Knowledge on security and safeguarding challenges in the Middle Eastern context

- Report writing skills in English.

- Fluency in Arabic

HOW TO APPLY:

The candidate will have to submit via email to info.em@cbm.org by 20th of April 2025:

- a consultant

- A Cover Sheet including the understanding of the assignment

- CV and/or CVs of all involved consultant(s) which clearly highlight qualifications as well as similar experiences including showcases

- A relevant and effective proposal including the scope of work as well as a working methodology demonstrating his/her technical capacity to lead this consultancy and to provide quality results.

- The methodology should show how the key elements of the identity (Vision, Mission, Objectives and Values) and governance of the organization will be at the forefront of the overall consultancy.

- The methodology should clearly show an effective communication method that facilitates the genuine participation of all evolved parties (CBM staff and key stakeholders)

- The duration of the assignment and an assignment implementation plan on a Gantt chart

Financial Offer

- Breakdown of consulting fees and other relevant costs